GRC WISDOM

Complete Enterprise Risk Management Module

Implementation Plan — with Feasibility & Realism Assessment

Prepared for internal engineering planning · July 2026

# Executive Assessment — Is This Plan Realistic?

Verdict:  The plan's engineering design is sound and correctly sequenced (RBAC and Audit Trail as the shared foundation before everything else). The main risk isn't the technical design — it's that the document contains zero effort/time estimates, and it implicitly commits to redoing this scope on top of storage and multi-tenancy assumptions that may not hold. Treat the estimates and sequencing notes below as the missing piece before this plan becomes a committed roadmap item.

## 1. What the plan gets right

- Correct dependency ordering: RBAC (WS2) before Audit Trail (WS1) before everything else is the right call — every other workstream needs to know who did the thing and whether they were allowed to.

- The audit entry / snapshot model (field-level diff, immutable log, version counter) is architecturally appropriate for SOC 2 CC7.2/CC8.1 and ISO 27001 A.5.28 — this is the same pattern mature GRC platforms use.

- Severity-tiered approval logic (Critical → CRO, High → Compliance, Moderate → Risk Owner) directly answers the client due-diligence gap flagged in the last review (Q7).

- Reusing the working Asset Register import pattern for Workstream 8, instead of inventing a new approach, is the right instinct — assuming that pattern is confirmed still functional (see Section 3).

- The verification plan (Part 7) gives testable, falsifiable acceptance criteria per workstream — this is genuinely unusual rigor for a prototype-stage codebase and should be preserved as-is.

## 2. What's missing: effort, timeline, and capacity reality

The source plan has no hours, days, or weeks anywhere in it — it is a scope document, not a schedule. Below is a realistic effort estimate per workstream, built from the complexity actually described in Part 4 (entities touched, endpoints added, UI surfaces changed), assuming a single senior full-stack developer working constrained hours (the working assumption established for this project's broader 6-month roadmap).

| Workstream | Scope driver | Realistic effort | Confidence |
| --- | --- | --- | --- |
| WS2 — RBAC Hierarchy | Permission matrix + middleware + refactor ~12 endpoints + frontend hook + retrofit every page's conditional UI | 18–24 hrs | Medium |
| WS1 — Universal Audit Trail | New DB structures × 2, diff engine, wraps every mutation across 5+ entity types, 2 new pages, per-entity history panel on 4 pages | 30–40 hrs | Medium |
| WS3 — Risk Lifecycle State Machine | 10-state machine, transition endpoint + validation, statusHistory model, UI wiring across 3 pages | 20–26 hrs | Medium |
| WS5 — Version History | Mostly rides on WS1's snapshot system; adds point-in-time query endpoint + diff/restore UI | 12–16 hrs | Medium-High |
| WS4 — Approval Workflow | Severity-tier routing, pendingChanges staging, 4 new endpoints, approval queue UI on 3 surfaces | 20–26 hrs | Medium |
| WS6 — Concurrent Edit Control | Lock API, optimistic concurrency (If-Match/409), UI lock banners + conflict modal | 14–20 hrs | Low-Medium — locking bugs are notoriously underestimated |
| WS7 — Evidence Management | Upload/list/download/delete, base64 in-memory storage (dev-only per the plan), 3 page integrations | 16–22 hrs | Medium |
| WS8 — Excel Import (Risk Register) | Template generation, validation endpoint, import endpoint, preview UI with per-row error surfacing | 16–22 hrs | Medium — this is the client's literal migration path, don't under-scope it |
| Integration testing, regression pass, polish | 8 workstreams touching the same server.ts and DataContext.tsx concurrently = high merge/regression surface | 16–24 hrs | Low — plan doesn't mention a regression suite existing |

Sum of point estimates: roughly 160–210 hours. Add a standard 20–25% integration/rework buffer for a plan that modifies one shared file (server.ts) across eight sequential workstreams, and the realistic range is 200–260 hours of focused engineering time — before QA, before the security/pen-test pass already planned for Month 4 of the broader roadmap, and before any client-facing UAT.

At constrained part-time hours (the pace used to produce the existing 6-month platform roadmap), 200–260 hours is roughly 2.5–4 months on its own. This workstream cannot be treated as a side task alongside the other Month 2–5 roadmap items (multi-tenancy, AI ingestion, PDPL/NCA ECC mapping, Arabic RTL, billing) without re-sequencing the overall roadmap — it needs to be slotted in explicitly, not assumed to run in parallel for free.

## 3. The load-bearing assumption that needs re-verification first

Flag:  This plan's Part 1 “What Actually Works Today” table states the 3-stage scoring pipeline is fully wired server-side and that Asset Register import genuinely reads uploaded files. A prior code audit of this same codebase found the third scoring stage (computePostTreatmentRRS) defined but never called, and — separately — found an upload handler that inserted hardcoded records instead of reading the file. If those findings have since been fixed, good; if this table is describing intended behavior rather than freshly re-verified behavior, the gap count above (G1–G15) may be understated. Recommend a 30-minute spot-check of the specific line references cited in Part 1 before this plan is finalized as a work order.

## 4. A sequencing risk the plan doesn't mention: storage durability

The code samples in Workstream 1 write directly to a DB.auditLog array (DB.auditLog.unshift(entry)), and Workstream 7 stores evidence as base64 strings in memory, explicitly flagged in the plan itself as “for dev; production → S3/blob.” This is consistent with the rest of the codebase running on an in-process object rather than a persisted, tenant-isolated database — the PostgreSQL + Row-Level Security migration is tracked separately on the broader roadmap and has not landed yet.

Building an elaborate audit trail, version history, and locking system on non-persistent, non-tenant-isolated storage means a meaningful share of this work (schema design, snapshot logic, lock semantics) will need to be re-validated — and in places rewritten — once the Postgres/RLS migration happens. Two honest options:

- Option A (recommended): Pull the Postgres + RLS migration forward to run immediately before or alongside WS1, so the audit/snapshot/lock tables are built on real, durable, tenant-isolated storage the first time.

- Option B: Proceed with WS1–WS8 on the current in-memory model as an explicitly-labeled prototype/demo milestone, with a known, budgeted re-implementation pass once Postgres lands. This is only acceptable if the client-facing SOC 2/ISO 27001 claims are not made against this milestone.

Whichever option is chosen, it should be a stated decision in the roadmap, not a silent assumption — this is exactly the kind of gap that turns into a client-facing surprise later.

## 5. Answers to the plan's open questions

Q1 — Risk appetite/tolerance configuration: Yes, but sequence it after WS1–WS4 land, not alongside. Appetite-breach detection is only meaningful once risk scores and statuses are trustworthy (audited, versioned, lifecycle-enforced) — building it earlier means re-testing it against a moving target.

Q2 — Risk categories/taxonomy: Yes, and it's small enough to fold into WS3 (Lifecycle) rather than run as a separate workstream — categoryId already exists as a field, this is primarily a reference-data + admin-UI task, estimated at 8-10 additional hours inside WS3.

Q3 — Notifications: Defer. It's a reasonable feature but has zero dependency on WS1-WS8 functioning correctly first, and adding email infrastructure mid-stream increases the surface area of this already-large change set. Revisit after Phase 5 (Part 6) closes.

Q4 — Sequential vs. parallel: Neither, exactly as scoped. Critical path first (WS2 → WS1 → WS3 → WS4) is correct and should stay strictly sequential — these all touch server.ts and DataContext.tsx and a parallel effort here is a merge-conflict and regression risk, not a time saver. WS6/WS7/WS8 (Phase 4) can genuinely run in parallel since they touch mostly-disjoint code paths, but only after the Section 4 storage-durability decision above is made — building the lock/evidence/import logic twice would be wasted effort.

# Part 1 — Current State Analysis

Methodology: grounded in ISO 31000:2018, COSO ERM 2017, SOC 2 Trust Services Criteria (CC7.2/CC8.1), and ISO 27001:2022 Annex A (A.5.28/A.8.9). Every gap below is intended to be verified against the actual codebase, not spec documents — see Section 3 of the Executive Assessment for a note on re-verifying the claims in the table immediately below.

## What Actually Works Today

| Capability | Status | Evidence |
| --- | --- | --- |
| Authentication (login/signup/JWT) | Real | server.ts L340-403 — real JWT signing, password verification |
| Risk CRUD (create/read/update/delete) | Real | server.ts L576-638 — protected endpoints, API calls from DataContext |
| 3-Stage Scoring Pipeline (IRS → CR → RRS → Post-Treatment) | Real | server.ts L530-572 — all 4 compute functions wired server-side |
| Control Library CRUD | Real | server.ts L679-731, ControlLibrary.tsx |
| Treatment Plan CRUD | Real | server.ts L733-785, TreatmentMonitor.tsx |
| Asset Register CRUD + Excel/CSV Import | Real | AssetRegister.tsx L100-223 — ExcelJS-based, actually reads file |
| Report Generation (role-based) | Partial | server.ts L474-527 — definitions + audit trail, no real file export |
| Dashboard with Heatmap | Real | Dashboard.tsx — but recomputes scores locally |
| 6-Role Type System | Defined | roles.ts — clean union type with all 6 roles |

## What Is Completely Missing (Every Gap)

| # | Gap | Severity | Affects |
| --- | --- | --- | --- |
| G1 | No audit trail anywhere — edits overwrite state directly with zero history | Critical | Every module. SOC 2 CC7.2/CC8.1, ISO 27001 A.5.28 |
| G2 | No version history / snapshots — cannot reconstruct register state on a past date | Critical | Risk Register, auditor requests |
| G3 | No approval workflow — edits apply immediately, “Approved” is not protected | Critical | Risk governance, audit artifact integrity |
| G4 | No risk lifecycle state machine — status is free-text-equivalent | High | ISO 31000 process compliance |
| G5 | RBAC not enforced at server level — scattered if-checks, no permission matrix | High | SOC 2 logical access, every module |
| G6 | No concurrent edit control — last-write-wins, silent data loss | High | Multi-user data integrity |
| G7 | No evidence management — cannot attach files to a risk or control | High | SOC 2 evidence requirements, audit |
| G8 | No risk register Excel import — asset import works, risk import path doesn't exist | Critical | Client migration path |
| G9 | No risk appetite/tolerance framework — no thresholds, no breach detection | Medium | COSO ERM Performance component |
| G10 | No risk categories/taxonomy — categoryId has no backing data or UI | Medium | ISO 31000 Context & Criteria |
| G11 | KRIs are client-side-only mock data — not persisted or API-linked | Medium | KRI monitoring, breach escalation |
| G12 | Documents are client-side-only mock data — no persistence, fake upload | Medium | Governance documentation |
| G13 | Frontend recomputes scores locally across 3 pages independently | Medium | Data consistency, performance |
| G14 | No real report export — endpoint returns JSON, no PDF/Excel | Low | Reporting, board presentations |
| G15 | No automated/scheduled report generation | Low | COSO ERM Information & Reporting |

# Part 2 — The Complete Risk Management Lifecycle

Per ISO 31000 and COSO ERM, the risk record must move through the following states end-to-end. (Rendered here as a transition table in place of the source document's Mermaid state diagram, which Word does not render natively.)

| From State | Trigger | To State | Note |
| --- | --- | --- | --- |
| (start) | Risk identified — any role | Draft |  |
| Draft | Submitted by Risk Owner | Pending Review | Requires reviewer assignment |
| Pending Review | Reviewed & scored | Assessed | Inherent score calculated |
| Assessed | Treatment required | Treatment Planning |  |
| Assessed | Within appetite | Accepted | Requires approval gate per severity tier |
| Treatment Planning | Treatment plans assigned | In Treatment |  |
| In Treatment | Treatment complete, needs verification | Under Review |  |
| Under Review | Controls verified effective | Accepted |  |
| Under Review | Controls insufficient | Treatment Planning |  |
| Accepted | Active monitoring period begins | Monitoring |  |
| Monitoring | Periodic review triggered | Under Review | KRI breach can also trigger this |
| Monitoring | Risk eliminated/no longer relevant | Closed |  |
| Accepted | Risk expired | Closed |  |

Every transition in this lifecycle must:

- Record WHO made the transition (user ID + name)

- Record WHEN (ISO timestamp)

- Record WHY (mandatory note for Accepted / Closed / Rejected)

- Create a snapshot of the full record state

- Be subject to role-based permission checks

# Part 3 — Role Hierarchy & Permission Matrix

## 3.1 Role Hierarchy (Organization-Scale)

The tool serves an organization, not 2–3 people. The hierarchy reflects real enterprise GRC structures:

| Level | Role | Scope |
| --- | --- | --- |
| 6 | Administrator | Full system access, user management, org configuration |
| 5 | CRO / Executive | Enterprise-wide risk oversight, approve Critical/High risks |
| 4 | Compliance Officer | Cross-functional compliance review, approve Medium risks |
| 3 | Risk Owner | Own and manage assigned risks, create treatment plans |
| 2 | Internal Auditor | Read-only access to everything, can create audit findings |
| 1 | Read-Only / Board Viewer | Dashboard and report access only |

## 3.2 Permission Matrix (RACI-Based)

| Action | Admin | CRO/Exec | Compliance | Risk Owner | Auditor | Board |
| --- | --- | --- | --- | --- | --- | --- |
| View Dashboard | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| View Risk Register | ✓ | ✓ | ✓ | ✓ (own) | ✓ | ✓ |
| Create Risk | ✓ | ✓ | ✓ | ✓ | — | — |
| Edit Risk | ✓ | ✓ | ✓ | ✓ (own) | — | — |
| Delete Risk | ✓ | — | — | — | — | — |
| Submit Risk for Review | ✓ | ✓ | ✓ | ✓ | — | — |
| Approve Critical Risk | ✓ | ✓ | — | — | — | — |
| Approve High Risk | ✓ | ✓ | ✓ | — | — | — |
| Approve Moderate/Low Risk | ✓ | ✓ | ✓ | ✓ | — | — |
| Create/Edit Controls | ✓ | ✓ | ✓ | ✓ | — | — |
| Create/Edit Treatments | ✓ | ✓ | ✓ | ✓ | — | — |
| Upload Evidence | ✓ | ✓ | ✓ | ✓ | ✓ | — |
| View Audit Log | ✓ | ✓ | ✓ | — | ✓ | — |
| Import from Excel | ✓ | ✓ | — | — | — | — |
| Export Reports | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| Manage Users | ✓ | — | — | — | — | — |
| View All Notifications | ✓ | ✓ | ✓ | Own only | ✓ | — |

# Part 4 — Detailed Implementation Workstreams

## Workstream 1: Universal Audit Trail (Gaps G1, G2)

SOC 2 CC7.2/CC8.1 · ISO 27001 A.5.28 · COSO ERM Information & Reporting

Principle: every mutation to any entity in the system — risk, control, treatment, asset, KRI, user, document — creates an immutable audit record. This is the single most important gap to close.

### What gets audited

- Who: user ID, name, role at time of action

- What: entity type, entity ID, action type, field-by-field changes (old value → new value)

- When: ISO 8601 timestamp, server-generated, not client-supplied

- Where: IP address, user agent (from request headers)

- Why: optional note, mandatory for approval/rejection/closure actions

### Data model addition to server.ts DB

auditLog: {

        id, entityType: 'risk'|'control'|'treatment'|'asset'|'kri'|'document'|'user'|'mapping',

        entityId, entityCode?, action: 'create'|'update'|'delete'|'approve'|'reject'|

          'submit'|'status_change'|'import'|'export'|'login'|'lock'|'unlock',

        userId, userName, userRole, ipAddress?, userAgent?, note?,

        fieldChanges: { field, oldValue, newValue }[],

        snapshotId?, timestamp

      }[]

       

      snapshots: {

        id, entityType, entityId, version,   // auto-incrementing per entity

        data,                                 // full JSON snapshot at this point

        createdBy, createdAt, trigger         // 'edit' | 'approve' | 'import' | 'status_change'

      }[]

### API endpoints

| Method | Endpoint | Purpose | Allowed roles |
| --- | --- | --- | --- |
| GET | /api/v1/audit-log | List all audit entries (filterable) | Admin, CRO, Compliance, Auditor |
| GET | /api/v1/audit-log?entityType=risk&entityId=:id | Audit history for specific entity | Admin, CRO, Compliance, Auditor |
| GET | /api/v1/audit-log?userId=:id | All actions by a specific user | Admin, Auditor |
| GET | /api/v1/:entityType/:id/history | Version history for an entity | All authenticated |
| GET | /api/v1/:entityType/:id/snapshots/:version | Specific point-in-time snapshot | All authenticated |
| GET | /api/v1/audit-log/export | Export audit log as CSV | Admin, Auditor |

### Frontend components

- Audit History Panel (reusable): chronological timeline, user + timestamp + action, expandable field-level diff, filterable — used on RiskDetail, ControlLibrary, TreatmentMonitor, AssetRegister

- Global Audit Log page (/audit-log): system-wide trail, filterable, exportable to CSV, visible only to Admin/CRO/Compliance/Auditor

## Workstream 2: RBAC Role Hierarchy (Gap G5)

SOC 2 Logical Access · ISO 27001 A.5.15/A.8.3

### Current problem

RBAC is enforced via scattered if-checks in server.ts, repeated roughly 12 times with slight variations — easy to forget on new endpoints, not centralized (a missed check is a security hole), and not granular enough to express “Risk Owner can edit own risks but not others.”

### Solution: centralized permission middleware

export const ROLE_LEVELS: Record<Role, number> = {

        "Administrator": 6, "CRO / Executive": 5, "Compliance Officer": 4,

        "Risk Owner": 3, "Internal Auditor": 2, "Read-Only / Board Viewer": 1,

      };

       

      export type Permission =

        | 'risk:create' | 'risk:read' | 'risk:update' | 'risk:delete'

        | 'risk:approve_critical' | 'risk:approve_high' | 'risk:approve_moderate'

        | 'risk:submit' | 'risk:import' | 'control:*' | 'treatment:*' | 'asset:*'

        | 'evidence:*' | 'audit:read' | 'audit:export'

        | 'report:generate' | 'report:export' | 'report:schedule'

        | 'user:manage' | 'user:read';

       

      export const ROLE_PERMISSIONS: Record<Role, Permission[]> = { /* full matrix, see Part 3.2 */ };

       

      const requirePermission = (...permissions) => (req, res, next) => {

        const userPermissions = ROLE_PERMISSIONS[req.user?.role] || [];

        if (!permissions.some(p => userPermissions.includes(p))) {

          createAuditEntry('system', 'access_denied', undefined, 'access_denied', req.user, null, null, req);

          return res.status(403).json({ error: `Your role does not have permission for this action.` });

        }

        next();

      };

       

      app.post("/api/v1/risks", authenticateToken, requirePermission('risk:create'), handler);

### Frontend permission helper

export function usePermissions() {

        const { currentRole } = useData();

        const can = (permission: Permission) => ROLE_PERMISSIONS[currentRole]?.includes(permission) ?? false;

        return { can, currentRole };

      }

      // if (can('risk:approve_critical')) { /* show Approve button */ }

## Workstream 3: Risk Lifecycle State Machine (Gap G4)

ISO 31000 Process · COSO ERM Performance

Current state: status is a free-form string union ('Open' | 'In Progress' | 'Closed' | 'Under Review') with no enforced transitions, no per-transition timestamps, and no approval gates.

### Target state machine

| State | Entry condition | Exit condition(s) | Who can transition |
| --- | --- | --- | --- |
| Draft | Risk created | → Pending Review | Risk Owner, Admin, CRO, Compliance |
| Pending Review | Submitted for assessment | → Assessed | Admin, CRO, Compliance |
| Assessed | Scores assigned | → Treatment Planning / Pending Approval | Admin, CRO, Compliance |
| Treatment Planning | Mitigation needed | → In Treatment | Risk Owner, Admin |
| In Treatment | Active treatment | → Under Review | Risk Owner, Admin |
| Under Review | Treatment verification | → Accepted / Treatment Planning | Admin, CRO, Compliance |
| Pending Approval | Needs formal acceptance | → Accepted / Rejected | Per severity tier |
| Accepted | Formally accepted | → Monitoring / Closed | Admin, CRO |
| Monitoring | Active watch | → Under Review / Closed | System/Admin |
| Closed | Risk resolved | Terminal (can reopen to Draft) | Admin, CRO, Compliance |

### Data model additions

statusHistory: { fromStatus, toStatus, changedBy, changedByName, changedAt, note? }[]

      approvalStatus: 'none'|'pending'|'approved'|'rejected'

      approvedBy?, approvedAt?, rejectedBy?, rejectedAt?, rejectedReason?

      pendingChanges?: object          // staged edits for approved risks (Workstream 4)

      currentReviewerId?, reviewDueDate?, lastReviewedAt?

      identifiedAt, assessedAt?, treatmentStartedAt?, acceptedAt?, closedAt?

### Transition enforcement — POST /api/v1/risks/:id/transition

Validates the target status against STATE_TRANSITIONS[current], checks role permission via canTransition(), requires a mandatory note for Accepted/Closed/Rejected, appends to statusHistory, stamps the relevant lifecycle timestamp, writes an audit entry, and recalculates dependent scores.

## Workstream 4: Approval Workflow Engine (Gap G3)

SOC 2 CC8.1 · ISO 27001 A.5.1

- New risks start as Draft — editable freely

- Submitted risks (Pending Review) get a reviewer assigned based on severity tier

- At approval stage, minimum approver is determined by score: Critical (>80) → CRO/Admin; High (51–80) → Compliance+; Moderate (21–50) → Risk Owner+; Low (≤20) → any authorized role

- Editing an Accepted risk stages changes in pendingChanges and moves the risk to Pending Approval; the original stays visible until approved

- Approval merges pendingChanges, creates a snapshot and audit entry; rejection clears pendingChanges and requires a reason

| Method | Endpoint | Purpose |
| --- | --- | --- |
| POST | /api/v1/risks/:id/submit | Submit Draft → Pending Review |
| POST | /api/v1/risks/:id/approve | Approve risk (with note) |
| POST | /api/v1/risks/:id/reject | Reject risk (mandatory reason) |
| GET | /api/v1/approvals/pending | All risks awaiting approval |
| GET | /api/v1/approvals/pending?role=:role | Pending approvals for a role tier |
| GET | /api/v1/approvals/history | Approval/rejection history |

Frontend: approval status badge + pending-changes diff + approve/reject buttons on RiskDetail; a “Pending Approvals” card on the Dashboard; an approval status column and filter tab on RiskRegister.

## Workstream 5: Version History & Snapshots (Gap G2)

SOC 2 CC7.2 · ISO 27001 A.5.28

Tightly coupled to Workstream 1 — every audit entry representing a mutation also creates a snapshot. Supports point-in-time reconstruction:

GET /api/v1/register-snapshot?date=2025-03-15T00:00:00Z

      // Returns, for each risk, the latest snapshot <= the requested date

Frontend: a History tab on RiskDetail showing a version timeline (v1, v2, v3…), side-by-side diff between any two versions, a non-destructive “Restore to this version” action, and a point-in-time full-record view.

## Workstream 6: Concurrent Edit Control (Gap G6)

Mechanism: optimistic locking + edit sessions.

risk.version = 1  // increments on every save

       

      POST /api/v1/locks { entityType: "risk", entityId: "r1" }

      // -> { lockId, expiresAt (5 min), heldBy: { userId, name } }

       

      PUT /api/v1/risks/:id   Headers: { "If-Match": "3" }

      // Server: is this user the lock holder (or expired)? does version match?

      // mismatch -> 409 Conflict, response includes current record to merge against

Frontend: acquire lock + “Editing…” indicator on edit mode; banner if another user holds the lock; re-acquire warning if the lock expires mid-edit; conflict modal on version mismatch; auto-release on navigate-away.

## Workstream 7: Evidence Management (Gap G7)

SOC 2 CC6.1 · ISO 27001 A.5.33

evidence: {

        id, entityType: 'risk'|'control'|'treatment'|'asset', entityId,

        fileName, fileSize, mimeType, description?,

        uploadedBy, uploadedByName, uploadedAt,

        base64Data   // in-memory storage for dev; production -> S3/blob

      }[]

| Method | Endpoint | Purpose |
| --- | --- | --- |
| POST | /api/v1/evidence | Upload evidence (multipart/form-data) |
| GET | /api/v1/evidence?entityType=risk&entityId=:id | List evidence for an entity |
| GET | /api/v1/evidence/:id/download | Download an evidence file |
| DELETE | /api/v1/evidence/:id | Remove evidence (audited) |

Frontend: file upload dropzone, evidence list (filename, size, uploader, date, description), download/delete with audit trail. Supported formats: PDF, DOCX, XLSX, PNG, JPG, CSV. Surfaces: RiskDetail, ControlLibrary, TreatmentMonitor.

## Workstream 8: Excel Import for Risk Register (Gap G8)

Client migration critical path

Replicates the Asset Register's working ExcelJS-based pattern: download template → upload & server-side validation → preview (valid rows green, invalid rows red with messages) → import with a create audit entry per row (trigger: 'import') and a snapshot.

### Risk column mapping

| Excel column | Maps to | Validation |
| --- | --- | --- |
| Risk Title* | title | Required, max 200 chars |
| Description* | description | Required |
| Likelihood* | likelihood | Integer 1–5 |
| Impact* | impact | Integer 1–5 |
| CIA – Confidentiality/Integrity/Availability | cia_c / cia_i / cia_a | Integer 1–5, default 3 |
| Status | status | Enum: Draft, Open, In Progress, Under Review, Closed |
| Category | categoryId | Must match existing category |
| Risk Owner | ownerId | Must match existing user email/name |
| Root Cause | rootCause | Free text |
| Treatment Strategy | treatmentStrategy | Enum: Accept, Mitigate, Transfer, Avoid |
| Target Date | targetDate | Valid date format |
| Service Tower / Comments | serviceTower / comments | Free text |

| Method | Endpoint | Purpose |
| --- | --- | --- |
| GET | /api/v1/risks/import/template | Download Excel template |
| POST | /api/v1/risks/import/validate | Validate file without importing |
| POST | /api/v1/risks/import | Import validated file |

### Import result response

{

        "imported": 15, "skipped": 3, "total": 18,

        "errors": [

          { "row": 4, "field": "likelihood", "message": "Value '7' is out of range (1-5)" },

          { "row": 8, "field": "ownerId", "message": "User 'john@company.com' not found" }

        ],

        "auditEntryId": "audit-12345"

      }

# Part 5 — File Change Map

| File | Workstream(s) | Change type |
| --- | --- | --- |
| server.ts | 1,2,3,4,5,6,7,8 | HEAVY MODIFY — audit infra, permission middleware, state machine, approvals, locking, evidence, import |
| src/types/roles.ts | 2 | MODIFY — ROLE_LEVELS, Permission type, ROLE_PERMISSIONS matrix |
| src/types/index.ts | 1,3,5,7 | MODIFY — extend Risk interface, add AuditEntry / Snapshot / Evidence types |
| src/store/DataContext.tsx | 1,2,3,4,6,7 | MODIFY — audit/approval/lock/evidence actions, usePermissions hook |
| src/pages/RiskDetail.tsx | 1,3,4,5,6,7 | HEAVY MODIFY — History tab, Approval panel, Evidence tab, Lock UI, Version diff |
| src/pages/RiskRegister.tsx | 3,8 | MODIFY — approval status column, Pending Approvals filter, Import button |
| src/pages/NewRisk.tsx | 3,6 | MODIFY — Draft/Submit workflow, lock acquisition on edit |
| src/pages/ControlLibrary.tsx | 1,7 | MODIFY — audit history per control, evidence tab |
| src/pages/TreatmentMonitor.tsx | 1 | MODIFY — audit history per treatment |
| src/pages/AssetRegister.tsx | 1 | MODIFY — audit history per asset |
| src/pages/Dashboard.tsx | 3,13 | MODIFY — Pending Approvals card, read scores from API not local compute |
| src/pages/ReportsView.tsx | 14 | MODIFY — real Excel export via ExcelJS + file-saver |
| src/components/Layout.tsx | 1 | MODIFY — add Audit Log nav item |
| src/App.tsx | 1 | MODIFY — add /audit-log route |
| src/pages/AuditLog.tsx | 1 | NEW — global audit log page |
| src/components/AuditTimeline.tsx | 1 | NEW — reusable audit history timeline |
| src/components/ApprovalPanel.tsx | 4 | NEW — approval status + action component |
| src/components/EvidencePanel.tsx | 7 | NEW — evidence upload/list component |
| src/components/ImportDialog.tsx | 8 | NEW — Excel import modal with validation preview |
| src/components/VersionDiff.tsx | 5 | NEW — side-by-side version comparison |
| src/services/auditService.ts | 1 | NEW — API client for audit endpoints |
| src/services/permissionService.ts | 2 | NEW — permission checking utilities |

21 files touched, one of them (server.ts) touched by all eight workstreams. This is the concrete basis for the merge/regression risk flagged in the Executive Assessment — a feature branch per workstream with a short-lived integration branch is strongly recommended over eight people (or one person, eight times) editing server.ts independently.

# Part 6 — Implementation Order & Dependencies

| Phase | Workstream(s) | Depends on | Can parallelize? |
| --- | --- | --- | --- |
| 1 | WS2 — RBAC Hierarchy | — (foundation) | No |
| 1 | WS1 — Universal Audit Trail | WS2 | No |
| 2 | WS3 — Risk Lifecycle | WS1 | Yes, with WS5 |
| 2 | WS5 — Version History | WS1 | Yes, with WS3 |
| 3 | WS4 — Approval Workflow | WS3 | No |
| 4 | WS6 — Concurrent Edit Control | WS1 | Yes, with WS7 & WS8 |
| 4 | WS7 — Evidence Management | WS1 | Yes, with WS6 & WS8 |
| 4 | WS8 — Excel Import | WS1 | Yes, with WS6 & WS7 |
| 5 | Integration testing, Dashboard updates, polish | WS4, WS5, WS6, WS7, WS8 | No |

Phase 1: WS2 → WS1 — the foundation everything else builds on. Phase 2: WS3 + WS5 in parallel. Phase 3: WS4, depends on WS3. Phase 4: WS6 + WS7 + WS8, independent of each other. Phase 5: integration testing, Dashboard updates, frontend polish.

See Executive Assessment Section 4 before starting Phase 1 — confirm the storage-durability decision (in-memory vs. Postgres/RLS) first, since it affects how WS1's schema should actually be built.

# Part 7 — Verification Plan

## Per-Workstream Acceptance Criteria

| WS | Test | How to verify |
| --- | --- | --- |
| 1 | Every mutation creates audit entry | Create/edit/delete a risk → /api/v1/audit-log shows entry with who/what/when/field changes |
| 1 | Snapshot created on every edit | Edit a risk 3 times → GET /api/v1/risks/:id/history returns 3 snapshots |
| 2 | Permission enforcement | Login as Board Viewer → POST /api/v1/risks → expect 403 |
| 2 | Type safety | npx tsc --noEmit → no role-related type errors |
| 3 | State transitions enforced | Attempt Draft → Closed directly → expect 400 |
| 3 | Timestamps recorded | Transition through full lifecycle → each statusHistory entry has a timestamp |
| 4 | Severity-tier approval | Create Critical risk → approve as Risk Owner → 403; approve as CRO → 200 |
| 4 | Staged edits on approved risks | Edit an Accepted risk → changes land in pendingChanges, not applied directly |
| 5 | Point-in-time reconstruction | Create 3 risks at different times → snapshot query for middle date returns only first 2 |
| 6 | Lock prevents concurrent edit | User A acquires lock → User B attempts edit → expect 423 Locked |
| 6 | Version conflict detected | User A saves version=2, but version=3 exists → expect 409 Conflict |
| 7 | Evidence attached with metadata | Upload file to risk → verify timestamp, uploader, file size recorded |
| 8 | Excel import reads real data | Upload .xlsx with 5 risks → verify all 5 appear with correct field values |
| 8 | Import validation catches errors | Upload file with invalid likelihood=7 → error reported, row not imported |

## End-to-End Scenario: Full Risk Lifecycle

- 1. Risk Owner logs in, creates risk “Data Center Fire” → status: Draft, audit entry created

- 2. Risk Owner submits for review → status: Pending Review, audit entry

- 3. Compliance Officer reviews, assigns scores (Likelihood=4, Impact=5) → status: Assessed

- 4. System computes IRS = 60 (High) → requires CRO approval for acceptance

- 5. Risk Owner creates treatment plan “Install fire suppression” → linked to risk

- 6. Status: Treatment Planning → In Treatment as work progresses

- 7. Treatment reaches 100% → Compliance Officer reviews → status: Under Review

- 8. CRO/Executive approves → status: Accepted, audit entry with approval note

- 9. 90 days later, periodic review triggered → status: Monitoring → Under Review

- 10. If risk no longer relevant → CRO closes → status: Closed, mandatory note

At every step: audit entry created, snapshot saved, timestamps recorded, permissions enforced.

# Open Questions — Recap

See Executive Assessment, Section 5, for recommended answers to all four questions raised in the source plan (risk appetite configuration, risk taxonomy, notifications, and sequential vs. parallel execution).